10/8/2019

Ray, Erin, Kim, Dr. Ray, and Roger.

Short term contract.  Kim completed and returned the contract.  Ray to process internally.

This short term contract will be used for student AT implementation and District training.

Perry Grant

Purpose is to deliver AT tools to District Teachers and to assist to identify future Professional Development initiatives.

Process:

Pre survey included in a Sunday night webinar registration.  Webinar will deliver IT and Office 365 content and include a post survery.  Follow-up webinar and survey in April.

Tasks:

Email from Erin delivered by the Superintendent to discuss the Perry Grant and the District’s involvement.  This will include a link to the presurvey and registration to the Sunday night webinar.

Sunday night webinar 10/27 (possibly several nights).

Possibly School delivered process.  Same process as Sunday night.

Plan for April posttest.

Check with Cheryl about school delivered pretest, webinar, posttest.   Hopefully she can gather a group to participate.

Check with TRC about 2 CTLE or clock hours PD for this activity.

9/17/19

Short-term contract.  Kim to update and send back to Ray

Technology Plan updates.  Updated.

Next Steps:

Review of Survey.

Discussion of

survey launch.

Webinar + school directed pre-survey + webinar + post-survey

Work meetings with Roger and Erin to create webinar content.

Next meeting 10/8.

Potential first webinar 10/20.

5/14/19

Erin, Kim, Sharon, Brennan –UB

Ray, Cheryl, Bryan –NFCSD

Next Steps from last meeting:

1. CSE Staff will update AT Categories List

In progress

2. CSE Staff will review both referral forms

Completed – see Teams.

3. UB Will try to screencast a few videos

Today’s work.

4. NFCSD Staff determine how to build capacity (use of forms, usefulness of AT) with staff.

In progress – need to develop a roll-out process, a mindset, a tiered schedule of meeting dates with staff / parents.

5. UB will send top 5 of broad AT supports.

UB to meet with NFCSD staff to work thru categories.  Erin to take an initial look to see gaps or identify suggestions.

6. Walk through eval at GPS with UB supports.

On hold.

Perry grant (if awarded)– customized / enhanced PD services.  Pre survey would be done at the start of PD / training.  Possibly use our NEEDS and/or Assessment survey.

Start o365 training potentially with a Sunday webinar.  Check with Rick about potentially openings for traditional PD.

Send Sharon our mock Assessment survey.

Reveal of 9 videos with Brennan.

Next meeting date......

Business – shortterm contract?